## Sheet1
Summary | Assignee | MD | Category | Category (SW) | Hours | Executed (EA) | Executed (Repeat Count) | Project Name (PMS) | Number of Test cases created / Re-worked | Due Date | Reporter
[VCU Entry GEM task 1] P2 execution- Nov 01 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 2 | 0 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/01/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] P3 execution- Nov 02 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 3 | 56 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/02/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] P2 execution for Bluetooth- Nov 03 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 5 | 96 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/03/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] Sanity execution- Nov 04 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-2. Sanity Test | 7 | 120 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/04/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] P2 execution- Nov 05 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 2 | 32 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/05/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] P3 execution- Nov 06 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 3 | 56 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/06/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] P2 execution for Bluetooth- Nov 07 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 5 | 96 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/07/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] Sanity execution- Nov 08 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-2. Sanity Test | 7 | 120 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/08/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] P2 execution- Nov 09 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 2 | 32 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/09/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] P3 execution- Nov 10 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 3 | 56 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/10/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] P2 execution for Bluetooth- Nov 11 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 5 | 96 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/11/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] Sanity execution- Nov 01 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 7 | 120 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/01/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 2] P2 execution- Nov 02 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 3 | 40 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/02/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 3] P3 execution- Nov 03 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 4 | 72 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/03/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 2] P2 execution for Bluetooth- Nov 04 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 6 | 120 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/04/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 2] Sanity execution- Nov 11 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-2. Sanity Test | 8 | 80 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/11/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 2] P2 execution- Nov 12 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 3 | 40 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/12/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 3] P3 execution- Nov 05 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 4 | 72 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/05/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 2] P2 execution for Bluetooth- Nov 06 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 6 | 15 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/06/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 2] Sanity execution- Nov 13 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-2. Sanity Test | 8 | 44 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/13/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 2] P2 execution- Nov 14 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 3 | 40 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/14/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 3] P3 execution- Nov 07 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 4 | 72 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/07/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 2] P2 execution for Bluetooth- Nov 08 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 6 | 40 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/08/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 1] Sanity execution- Nov 15 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-2. Sanity Test | 1 | 0 | 1 | GM AVN_VCU ENTRY GEM MY28 | 0 | 11/15/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] Sanity execution- Nov 16 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-2. Sanity Test | 3 | 56 | 3 | GM AVN_VCU ENTRY GEM MY29 | 0 | 11/16/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] Sanity execution- Nov 17 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 6 | 96 | 1 | GM AVN_VCU ENTRY GEM MY30 | 0 | 11/17/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] P2 execution- Nov 01 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 4 | 90 | 1 | GM AVN_VCU ENTRY GEM MY31 | 0 | 11/01/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 1] P3 execution- Nov 18 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 4 | 32 | 1 | GM AVN_VCU ENTRY GEM MY32 | 0 | 11/18/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] Sanity execution- Nov 19 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-2. Sanity Test | 7 | 56 | 2 | GM AVN_VCU ENTRY GEM MY33 | 0 | 11/19/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] Sanity execution- Nov 02 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-2. Sanity Test | 8 | 96 | 2 | GM AVN_VCU ENTRY GEM MY34 | 0 | 11/02/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 1] P2 execution- Nov 20 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 2 | 120 | 1 | GM AVN_VCU ENTRY GEM MY35 | 0 | 11/20/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] P3 execution- Nov 03 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 4 | 32 | 2 | GM AVN_VCU ENTRY GEM MY36 | 0 | 11/03/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 1] P2 execution for Bluetooth- Nov 04 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 6 | 56 | 1 | GM AVN_VCU ENTRY GEM MY37 | 0 | 11/04/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 1] Sanity execution- Nov 21 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-2. Sanity Test | 1 | 96 | 1 | GM AVN_VCU ENTRY GEM MY38 | 0 | 11/21/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 2] Sanity execution- Nov 05 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-2. Sanity Test | 3 | 120 | 2 | GM AVN_VCU ENTRY GEM MY39 | 0 | 11/05/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 3] Sanity execution- Nov 22 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-2. Sanity Test | 2 | 40 | 1 | GM AVN_VCU ENTRY GEM MY40 | 0 | 11/22/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 2] Sanity execution- Nov 23 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-2. Sanity Test | 5 | 72 | 2 | GM AVN_VCU ENTRY GEM MY41 | 0 | 11/23/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 2] Sanity execution- Nov 24 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-2. Sanity Test | 7 | 120 | 1 | GM AVN_VCU ENTRY GEM MY42 | 0 | 11/24/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 2] P2 execution- Nov 25 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 4 | 144 | 2 | GM AVN_VCU ENTRY GEM MY43 | 0 | 11/25/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 3] P3 execution- Nov 26 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 4 | 40 | 1 | GM AVN_VCU ENTRY GEM MY44 | 0 | 11/26/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 2] P2 execution for Bluetooth- Nov 06 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 6 | 72 | 1 | GM AVN_VCU ENTRY GEM MY45 | 0 | 11/06/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 2] Sanity execution- Nov 27 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-2. Sanity Test | 2 | 120 | 1 | GM AVN_VCU ENTRY GEM MY46 | 0 | 11/27/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 2] P2 execution- Nov 28 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-12. Function Test | 2 | 78 | 2 | GM AVN_VCU ENTRY GEM MY47 | 0 | 11/28/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 3] Sanity execution- Nov 07 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-2. Sanity Test | 5 | 40 | 2 | GM AVN_VCU ENTRY GEM MY48 | 0 | 11/07/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 2] Sanity execution- Nov 29 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-2. Sanity Test | 8 | 72 | 2 | GM AVN_VCU ENTRY GEM MY49 | 0 | 11/29/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 2] Sanity execution- Nov 30 | Arun Kumar arun.kumar | 0.256 | Validation Test | 5-2. Sanity Test | 6 | 120 | 1 | GM AVN_VCU ENTRY GEM MY50 | 0 | 11/30/2024 | Arun Kumar arun.kumar
[VCU Entry GEM task 1] P2 execution- Nov 09 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 2 | 0 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 2024-09-11 | Kavya Naik kavya.naik
[VCU Entry GEM task 1] P3 execution- Nov 10 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 3 | 56 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 2024-10-11 | Kavya Naik kavya.naik
[VCU Entry GEM task 1] P2 execution for Bluetooth- Nov 11 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 5 | 96 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 2024-11-11 | Kavya Naik kavya.naik
[VCU Entry GEM task 1] Sanity execution- Nov 08 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-2. Sanity Test | 7 | 120 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 2024-08-11 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 1] P2 execution- Nov 12 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 2 | 32 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 2024-12-11 | Kavya Naik kavya.naik
[VCU Entry GEM task 1] P3 execution- Nov 09 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 3 | 56 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 2024-09-11 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 1] P2 execution for Bluetooth- Nov 13 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 5 | 96 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/13/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 1] Sanity execution- Nov 10 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-2. Sanity Test | 7 | 120 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 2024-10-11 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 1] P2 execution- Nov 11 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 2 | 32 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 2024-11-11 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 1] P3 execution- Nov 14 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 3 | 56 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/14/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 1] P2 execution for Bluetooth- Nov 15 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 5 | 96 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/15/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 1] Sanity execution- Nov 16 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 7 | 120 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/16/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 2] P2 execution- Nov 12 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 3 | 40 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 2024-12-11 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 3] P3 execution- Nov 17 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 4 | 72 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/17/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 2] P2 execution for Bluetooth- Nov 18 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 6 | 120 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/18/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 2] Sanity execution- Nov 13 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-2. Sanity Test | 8 | 80 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/13/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 2] P2 execution- Nov 14 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 3 | 40 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/14/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 3] P3 execution- Nov 19 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 4 | 72 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/19/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 2] P2 execution for Bluetooth- Nov 20 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 6 | 15 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/20/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 2] Sanity execution- Nov 21 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-2. Sanity Test | 8 | 44 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/21/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 2] P2 execution- Nov 22 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 3 | 40 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/22/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 3] P3 execution- Nov 15 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 4 | 72 | 1 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/15/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 2] P2 execution for Bluetooth- Nov 16 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 6 | 40 | 2 | GM AVN_VCU ENTRY GEM MY26 | 0 | 11/16/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 1] Sanity execution- Nov 17 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-2. Sanity Test | 1 | 0 | 1 | GM AVN_VCU ENTRY GEM MY28 | 0 | 11/17/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 1] Sanity execution- Nov 23 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-2. Sanity Test | 3 | 56 | 3 | GM AVN_VCU ENTRY GEM MY29 | 0 | 11/23/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 1] Sanity execution- Nov 18 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 6 | 96 | 1 | GM AVN_VCU ENTRY GEM MY30 | 0 | 11/18/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 1] P2 execution- Nov 19 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 4 | 90 | 1 | GM AVN_VCU ENTRY GEM MY31 | 0 | 11/19/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 1] P3 execution- Nov 20 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 4 | 32 | 1 | GM AVN_VCU ENTRY GEM MY32 | 0 | 11/20/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 1] Sanity execution- Nov 24 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-2. Sanity Test | 7 | 56 | 2 | GM AVN_VCU ENTRY GEM MY33 | 0 | 11/24/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 1] Sanity execution- Nov 25 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-2. Sanity Test | 8 | 96 | 2 | GM AVN_VCU ENTRY GEM MY34 | 0 | 11/25/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 1] P2 execution- Nov 20 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 2 | 120 | 1 | GM AVN_VCU ENTRY GEM MY35 | 0 | 11/20/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 1] P3 execution- Nov 26 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-12. Function Test | 4 | 32 | 2 | GM AVN_VCU ENTRY GEM MY36 | 0 | 11/26/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 1] P2 execution for Bluetooth- Nov 21 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 6 | 56 | 1 | GM AVN_VCU ENTRY GEM MY37 | 0 | 11/21/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 1] Sanity execution- Nov 22 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-2. Sanity Test | 1 | 96 | 1 | GM AVN_VCU ENTRY GEM MY38 | 0 | 11/22/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 2] Sanity execution- Nov 27 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-2. Sanity Test | 3 | 120 | 2 | GM AVN_VCU ENTRY GEM MY39 | 0 | 11/27/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 3] Sanity execution- Nov 28 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-2. Sanity Test | 2 | 40 | 1 | GM AVN_VCU ENTRY GEM MY40 | 0 | 11/28/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 2] Sanity execution- Nov 29 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-2. Sanity Test | 5 | 72 | 2 | GM AVN_VCU ENTRY GEM MY41 | 0 | 11/29/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 2] Sanity execution- Nov 30 | Kavya Naik kavya.naik | 0.256 | Validation Test | 5-2. Sanity Test | 7 | 120 | 1 | GM AVN_VCU ENTRY GEM MY42 | 0 | 11/30/2024 | Kavya Naik kavya.naik
[VCU Entry GEM task 2] P2 execution- Nov 23 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 4 | 144 | 2 | GM AVN_VCU ENTRY GEM MY43 | 0 | 11/23/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 3] P3 execution- Nov 24 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 4 | 40 | 1 | GM AVN_VCU ENTRY GEM MY44 | 0 | 11/24/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 2] P2 execution for Bluetooth- Nov 25 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 6 | 72 | 1 | GM AVN_VCU ENTRY GEM MY45 | 0 | 11/25/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 2] Sanity execution- Nov 26 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-2. Sanity Test | 2 | 120 | 1 | GM AVN_VCU ENTRY GEM MY46 | 0 | 11/26/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 2] P2 execution- Nov 27 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-12. Function Test | 2 | 78 | 2 | GM AVN_VCU ENTRY GEM MY47 | 0 | 11/27/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 3] Sanity execution- Nov 28 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-2. Sanity Test | 5 | 40 | 2 | GM AVN_VCU ENTRY GEM MY48 | 0 | 11/28/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 2] Sanity execution- Nov 29 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-2. Sanity Test | 8 | 72 | 2 | GM AVN_VCU ENTRY GEM MY49 | 0 | 11/29/2024 | Anitha Kanavli anitha.kanavli
[VCU Entry GEM task 2] Sanity execution- Nov 30 | Anitha Kanavli anitha.kanavli | 0.256 | Validation Test | 5-2. Sanity Test | 6 | 120 | 1 | GM AVN_VCU ENTRY GEM MY50 | 0 | 11/30/2024 | Anitha Kanavli anitha.kanavli